GREENLANG PLATFORM

V2/V2.1 Re-Audit Report

Sprint 0-6 Execution Verification

_______________________________________________

Prepared for: Akshay Makar, CEO

Audit Date: April 2, 2026

Classification: Internal / Confidential

# 1. Executive Summary

This re-audit verifies whether the V2/V2.1 execution plan (Sprints 0-6) has been fully implemented. The audit examines the live codebase as of April 2, 2026, checking every deliverable against the sprint plan.

CRITICAL FINDING: The V2.1 React SPA shell (the centerpiece of the execution plan) has NOT been built. The primary user interface at localhost:8000 remains vanilla HTML workspaces served by FastAPI. No frontend/ directory exists at repo root. The React enterprise shell promised in Sprints 2-4 does not exist as a unified product.

## 1.1 Sprint Completion Matrix

| Sprint | Status | Finding |
| --- | --- | --- |
| Sprint 0: Evidence Re-Audit | PARTIAL | No standalone audit runner script. Audit functions embedded in CLI (v2 gate). No audit_delta_report.md found. |
| Sprint 1: V2 Truth Fixes | DONE | V2 closure gates show PASSED. 6 native V2 backends exist. CBAM/CSRD/VCCI use hybrid native+V1 fallback (intentional). 30 agents registered. |
| Sprint 2: React Frontend Shell | NOT STARTED | NO frontend/ directory at repo root. No React SPA shell. No shared design system package. FastAPI still serves vanilla HTML. No SPA fallback routing. |
| Sprint 3: Workspace Migration | NOT STARTED | No React workspace components (CBAMWorkspace.tsx etc.) connected to shell. React apps exist in individual applications/ dirs but are completely disconnected from localhost:8000. |
| Sprint 4: Enterprise UX | NOT STARTED | No command palette, no run graph explorer, no artifact diff viewer, no governance center, no role-based views, no WebSocket real-time updates. |
| Sprint 5: CI + Release Train | DONE | 4 V2 CI workflows configured and blocking. Two consecutive green release train cycles documented. Vitest configured in app frontends. |
| Sprint 6: Closure | DONE | GO_NO_GO_RECORD signed. IMMUTABLE_EVIDENCE_MANIFEST with 43 SHA256 hashes. RC soak log complete. Phase 0-6 gate statuses all passed. |

# 2. What IS Complete

## 2.1 V2 Platform Infrastructure (Sprints 0-1, 5-6)

The V2 platform backbone is solid and fully evidenced:

- All 7 V2 closure gates show PASSED with timestamps (v2_closure_report.json)

- 6 native V2 runtime_backend.py files exist for all apps (EUDR/GHG/ISO14064 are pure native; CBAM/CSRD/VCCI use hybrid native-first + V1 fallback)

- 30 agents registered in v2_agent_registry.yaml across 8 domains (24 production, 3 qualified, 2 incubating, 1 retired)

- 50 packs deployed across 4 quality tiers with lifecycle enforcement

- 5 Rego policy bundles enforced (authz, pack trust, tier policy, egress, data controls)

- 4 V2 CI workflows: platform-ci, security-governance-ci, release-train, frontend-ux-ci

- Two consecutive green release train cycles documented in RELEASE_TRAIN_CYCLE_LOG.md

- IMMUTABLE_EVIDENCE_MANIFEST.json with 43 artifact SHA256 hashes

- Complete Phase 0-6 gate evidence chain

- 18+ V2 governance documents including platform handbook, migration playbooks, on-call/SLOs

## 2.2 Vanilla HTML Workspaces (Functional, Not Modernized)

The HTML workspaces at localhost:8000 are functional and have been significantly improved since the first audit:

| Workspace | Lines | Features |
| --- | --- | --- |
| CBAM | 1,003 | Dual-file upload, 4-column stats, drilldown gap analysis, validation cards, compliance badges, artifact downloads, ZIP export |
| CSRD | 306 | Drag-drop upload, status chips, results card, artifact list, ZIP bundle, error handling |
| VCCI | 306 | File upload, validation badges, compliance scoring, artifact download, bundle export |
| EUDR | 490 | Supplier risk heatmap, risk distribution bar chart, supplier analysis table, policy verdict, metric grid, progress bar |
| GHG | 331 | Scope 1/2/3 breakdown visualization, emissions intensity metrics, color-coded scope bars, policy verdict |
| ISO14064 | 336 | SVG conformance ring, verification checklist, control pass/fail counts, dynamic color thresholds, policy verdict |
| Shell | 236 | Multi-app card navigation, dark theme, responsive grid layout, feature pills |

## 2.3 React Apps (Exist But Disconnected)

Sophisticated React applications exist inside individual application directories but are NOT connected to the main shell at localhost:8000:

- GL-EUDR-APP: React 18 + TypeScript + MUI v5 + Redux + Recharts + Leaflet maps (7 routes, 23 components, 12,674 lines)

- GL-GHG-APP: React 18 + TypeScript + MUI v5 + Redux + Recharts (8 routes, 33 components, 12,200 lines)

- GL-ISO14064-APP: React 18 + TypeScript + MUI v5 + Redux (37 components, 13,702 lines)

- GL-VCCI-Carbon-APP: React 18 + TypeScript + MUI v5 + Redux (19 components, 11,945 lines)

- GL-Agent-Factory: React 18 + TypeScript + Tailwind + Radix UI + Zustand + React Query (22 components, 15,947 lines)

These React apps run on separate dev servers (port 3000) and proxy API calls to localhost:8000. They are fully functional applications with forms, charts, state management, and rich UI. However, a user visiting localhost:8000 cannot access ANY of them.

# 3. What Is NOT Done (The V2.1 Gap)

## 3.1 Sprint 2: React SPA Shell - NOT BUILT

The V2.1 execution plan called for a unified React shell at repo root (frontend/) that would replace the vanilla HTML workspaces. This is the single biggest undelivered item:

- No frontend/ directory exists at repo root

- No shared design system package (@greenlang/ui or similar)

- No unified route framework (/apps/cbam, /csrd, etc. in React)

- No SPA fallback in FastAPI (still serves individual HTML files per route)

- No app switcher, no unified navigation bar, no breadcrumbs in React

- The 5 existing React apps each have their own independent design systems and are not unified

## 3.2 Sprint 3: Workspace Migration - NOT DONE

The plan called for migrating all 6 HTML workspaces into React components within the unified shell:

- No CBAMWorkspace.tsx, CSRDWorkspace.tsx, VCCIWorkspace.tsx, EUDRWorkspace.tsx, GHGWorkspace.tsx, ISO14064Workspace.tsx connected to a shell

- The GL-Agent-Factory has React pages for CBAM and EUDR (CBAMCalculator.tsx, EUDRCompliance.tsx) but these are independent applications, not migrated workspace components

- Users at localhost:8000 still interact with vanilla HTML with inline JavaScript

## 3.3 Sprint 4: Enterprise UX Features - NOT BUILT

| Feature | Status | Finding |
| --- | --- | --- |
| Command Palette (Cmd+K) | MISSING | No CommandPalette component. No keyboard shortcut handlers. No global search overlay. |
| Run Graph Explorer (DAG) | MISSING | No pipeline DAG visualization. No react-flow or cytoscape dependency. Only linear progress bars. |
| Artifact Diff Viewer | MISSING | No run-vs-run comparison UI. No diff rendering. Users can only download artifacts. |
| Governance Center | MISSING | No pack tier browser, no agent lifecycle viewer, no policy inspector in shell. |
| Role-Based Views | PARTIAL | GL-Agent-Factory has admin/analyst/viewer/api_user roles in types.ts. But no RBAC enforcement, no persona switching in shell. |
| Real-Time Operations | MISSING | No WebSocket connections. Progress is simulated with setTimeout intervals. No live connector health. |
| WCAG AA Accessibility | PARTIAL | Radix UI provides base accessibility in GL-Agent-Factory. HTML workspaces have no WCAG audit. No high contrast mode. |

# 4. The Architecture Gap

## 4.1 Two Disconnected UI Worlds

The codebase has two completely separate UI architectures that do not communicate:

### World 1: Vanilla HTML Shell (What Users See)

- Served by FastAPI at localhost:8000

- 7 HTML files + 2 shared JS files (3,008 total lines)

- Inline CSS with dark theme, inline JavaScript for interactivity

- No build step, no component reuse, no state management

- Functional but not enterprise-grade

### World 2: React Applications (Unreachable by Users)

- 5+ independent React apps in applications/*/frontend/

- 66,468+ total lines of TypeScript/React code

- Full MUI v5 design system, Redux state, Recharts visualizations

- Each runs on its own Vite dev server (port 3000)

- Cannot be accessed from localhost:8000 - completely disconnected

The V2.1 execution plan was specifically designed to bridge these two worlds by creating a unified React shell that would replace the vanilla HTML and incorporate the best components from the individual React apps. This bridge has not been built.

# 5. Honest Assessment

## 5.1 What Your CTO Delivered Well

- V2 platform infrastructure is genuinely complete and well-governed

- All 6 V2 backends work and produce contract-compliant artifacts

- CI/CD and release train processes are mature with real evidence

- Governance documentation is comprehensive (18+ documents, immutable evidence)

- HTML workspaces are functional with domain-specific visualizations

- Agent registry, pack tiering, and policy enforcement are operational

## 5.2 What Was Not Delivered

- The entire V2.1 frontend modernization (Sprints 2-4) was not executed

- No unified React shell exists - users still see vanilla HTML

- No enterprise UX features (command palette, DAG explorer, diff viewer, governance center)

- The sophisticated React apps (66,000+ lines) remain stranded in application directories

- The execution plan promised 9 weeks of frontend work - this work was not done

## 5.3 Overall Completion Score

| Dimension | Planned | Actual | Gap |
| --- | --- | --- | --- |
| V2 Platform/Backend | 100% | DONE | Complete. All gates passed, all backends live. |
| V2 Governance/Docs | 100% | DONE | Complete. 18+ docs, immutable evidence, release trains. |
| V2 CI/CD/Tests | 100% | DONE | Complete. 4 workflows, 2 green cycles, visual regression. |
| V2.1 React Shell | 100% | NOT STARTED | frontend/ does not exist. No SPA. No shared design system. |
| V2.1 Workspace Migration | 100% | NOT STARTED | All workspaces remain vanilla HTML. |
| V2.1 Enterprise UX | 100% | NOT STARTED | No command palette, DAG, diff, governance, roles. |

V2 is done. V2.1 frontend modernization is not started.

# 6. Recommended Path Forward

The V2 platform is genuinely strong. The gap is entirely frontend. Here is the recommended approach:

## 6.1 Option A: Build the React Shell (6-8 Weeks)

Execute Sprints 2-4 as originally planned. The building blocks already exist (66,000+ lines of React code across 5 apps). The work is integration and unification, not greenfield development.

- Week 1-2: Scaffold frontend/ with Vite + React 18 + TypeScript + MUI v5. Build shell layout, app switcher, route framework. Mount in FastAPI.

- Week 3-4: Migrate CBAM/CSRD/VCCI HTML workspaces to React. Port EUDR/GHG/ISO14064 using existing React app components as foundation.

- Week 5-6: Build enterprise features (command palette, run graph, artifact diff, governance center).

- Week 7-8: Frontend CI/CD, WCAG AA, visual regression, release train with React.

## 6.2 Option B: Ship V2 As-Is, Plan V3 Frontend (Faster)

Accept that V2 is a platform release (infrastructure, backends, governance) and position the React shell as V3. The current HTML workspaces are functional for demos and pilot customers.

- Pro: Ship immediately, no delay

- Con: Users see vanilla HTML, not enterprise-grade UX

- Con: 66,000+ lines of React code remain unused

## 6.3 How to Frame This

"V2 platform and backend are complete and well-governed. The V2.1 frontend modernization (unified React shell with enterprise UX) was planned but not executed. The HTML workspaces are functional for current needs. We recommend a dedicated 6-8 week frontend sprint to unify the existing React applications into the enterprise shell that matches our platform ambition."

# 7. Final Verdict

| Component | Status | Verdict |
| --- | --- | --- |
| MVP | DONE | Fully complete. GO_FOR_PILOT locked. No changes needed. |
| V1 | DONE | Fully complete. 3 apps production-ready. Closure decision GO. |
| V2 Platform | DONE | Infrastructure, backends, packs, agents, governance, CI all complete. All 7 gates PASSED. |
| V2 HTML UI | DONE | Functional workspaces with domain visualizations for all 6 apps. Not enterprise-grade but usable. |
| V2.1 React Shell | NOT STARTED | No frontend/ directory. No unified SPA. No shared design system. React apps exist but disconnected. |
| V2.1 Enterprise UX | NOT STARTED | No command palette, DAG explorer, artifact diff, governance center, role-based views. |

BOTTOM LINE: MVP, V1, and V2 platform are genuinely complete. Your CTO delivered solid infrastructure. However, the V2.1 frontend modernization (the React enterprise shell that would make the UI "10 years ahead") has not been started. The 66,000+ lines of React code exist as raw materials but have not been assembled into the unified product experience. The current user-facing interface remains vanilla HTML served by FastAPI.

_______________________________________________

End of Re-Audit Report